## Defect Report
Tichi Web Application (Staging) — Login & Sign Up Modules — Defect Report
Prepared by: QA Engineer - Manual Testing Team ¦ Application URL: https://tichi-app-webapp-stage.web.app
Defect ID | Related Test Case ID | Module | Defect Title | Defect Summary | Detailed Description | Preconditions | Steps to Reproduce | Test Data | Expected Result | Actual Result | Severity | Priority | Environment | Browser | Operating System | Build Version | Status | Reported By | Reported Date | Screenshot Placeholder | Developer Comments
BUG_001 | TC_LOGIN_007 | Login | Application allows login with invalid email format | The Login module accepts invalid/malformed email addresses in the Email field and proceeds with authentication instead of blocking the request with a validation error. | The Email input field on the Login screen does not perform client-side or server-side validation for correct email syntax (e.g., missing '@', missing domain, multiple '@' symbols). Users are able to submit clearly invalid email strings and the system attempts login instead of rejecting the input immediately with a field-level error message. This bypasses standard email format validation (RFC 5322) and could allow malformed data to reach the backend authentication service, leading to inconsistent data handling and a poor user experience. | 1. User is on the Login page of the Tichi web application. 2. User does not have an active session. | 1. Navigate to https://tichi-app-webapp-stage.web.app 2. Click on the 'Login' tab/link. 3. In the Email field, enter an invalid email format (e.g., 'testuser123' or 'test@@com' or 'test@com'). 4. Enter any password in the Password field (e.g., 'Test@1234'). 5. Click the 'Login' button. 6. Observe system behavior. | Email: testuser123 (no @ symbol) Email: test@@example.com (double @) Email: test@com (no top-level domain) Password: Test@1234 | The system should validate the email field format on blur/submit and display an inline error message such as 'Please enter a valid email address.' The Login API call should not be triggered, and the user should remain on the Login page. | No client-side validation error is displayed. The form submits the invalid email to the backend. Depending on backend response, the user either receives a generic 'Invalid credentials' message (indicating the malformed email was still processed as a login attempt) or, in some cases, is allowed to proceed, confirming the absence of proper email format validation. | High | High | Staging (https://tichi-app-webapp-stage.web.app) | Google Chrome v.126.0 (Latest) | Windows 11 (64-bit) | Build 1.4.2-stage | Open | QA Engineer - Manual Testing Team | 2026-06-18 | [Screenshot_BUG_001.png - to be attached] | Confirmed. Email regex validation missing on frontend; backend also does not validate format. Fix scheduled for next sprint.
BUG_002 | TC_SIGNUP_003 | Sign Up | Sign Up form accepts invalid email format without validation error | Similar to the Login module, the Sign Up form's Email field does not validate email syntax before allowing account creation to proceed. | When registering a new account, the Email field on the Sign Up page does not check for a valid email pattern. Users can enter strings without '@', without a domain, or with invalid characters, and the 'Sign Up' button remains enabled and submits the form. This could result in unusable accounts being created with unreachable/invalid email addresses, breaking downstream features such as email verification and password recovery. | 1. User is on the Sign Up page. 2. User has no existing account with the test data used. | 1. Navigate to https://tichi-app-webapp-stage.web.app 2. Click 'Sign Up'. 3. Enter Full Name: 'John Tester'. 4. Enter Email: 'johntester.com' (missing @ symbol). 5. Enter Password: 'Passw0rd!23'. 6. Confirm Password: 'Passw0rd!23'. 7. Click 'Sign Up' / 'Create Account' button. | Full Name: John Tester Email: johntester.com Password: Passw0rd!23 | System should display an inline validation error ('Please enter a valid email address') and prevent form submission until a valid email is entered. | Form is submitted without any validation error. Account creation request is sent to the server with the invalid email. | High | High | Staging (https://tichi-app-webapp-stage.web.app) | Google Chrome v.126.0 (Latest) | Windows 11 (64-bit) | Build 1.4.2-stage | Open | QA Engineer - Manual Testing Team | 2026-06-18 | [Screenshot_BUG_002.png - to be attached] | Duplicate root cause of BUG_001; will be fixed together as part of shared validation utility.
BUG_003 | TC_LOGIN_012 | Login | No account lockout after multiple consecutive failed login attempts | The system does not lock or temporarily restrict a user account after repeated failed login attempts, exposing the application to brute-force attacks. | Industry best practice requires accounts to be temporarily locked or throttled (e.g., CAPTCHA, delay, lockout) after a defined number of consecutive failed login attempts (typically 5). Testing shows the Login form allows unlimited login attempts with incorrect passwords without any lockout, delay, or CAPTCHA challenge, creating a security vulnerability. | 1. A valid registered account exists (e.g., qa.tester@example.com). 2. User is on the Login page. | 1. Navigate to the Login page. 2. Enter a valid registered email address. 3. Enter an incorrect password. 4. Click 'Login'. 5. Repeat steps 2-4 at least 10 times consecutively. 6. Observe system behavior after the 5th, 8th, and 10th attempts. | Email: qa.tester@example.com Password (incorrect, repeated): WrongPass1! | After 5 consecutive failed attempts, the account should be temporarily locked (e.g., for 15 minutes) or a CAPTCHA/verification challenge should be triggered, with a clear message shown to the user. | The system allows unlimited login attempts with no lockout, delay, or CAPTCHA challenge at any point during 10+ attempts. | Critical | High | Staging (https://tichi-app-webapp-stage.web.app) | Google Chrome v.126.0 (Latest) | Windows 11 (64-bit) | Build 1.4.2-stage | Open | QA Engineer - Manual Testing Team | 2026-06-19 | [Screenshot_BUG_003.png - to be attached] | Acknowledged as a security gap. Escalated to security team for rate-limiting/lockout implementation.
BUG_004 | TC_LOGIN_005 | Login | Password field does not mask input when 'Show Password' toggle is rapidly clicked | Rapidly toggling the 'Show/Hide Password' eye icon causes the password text to remain visible even after switching back to hidden mode. | The password visibility toggle icon on the Login form is expected to switch the input type between 'password' and 'text'. When the icon is clicked rapidly multiple times in succession, the field's masking state becomes inconsistent — text remains visible in plain form even though the icon indicates 'hidden' state. | 1. User is on the Login page. 2. Password field contains text. | 1. Navigate to the Login page. 2. Type a password into the Password field (e.g., 'MySecret123!'). 3. Click the 'Show Password' eye icon 8-10 times rapidly. 4. Observe the final state of the input field and the icon. | Password: MySecret123! | The password field should toggle cleanly between masked (dots/asterisks) and unmasked (plain text) state, consistently matching the icon state after each click. | After rapid clicking, the icon shows 'hidden' (closed eye) state, but the password remains visible in plain text in the input field. | Medium | Medium | Staging (https://tichi-app-webapp-stage.web.app) | Google Chrome v.126.0 (Latest) | Windows 11 (64-bit) | Build 1.4.2-stage | Open | QA Engineer - Manual Testing Team | 2026-06-19 | [Screenshot_BUG_004.png - to be attached] | Reproducible only in Chrome; investigating event debounce on icon click handler.
BUG_005 | TC_SIGNUP_008 | Sign Up | Weak passwords (e.g., '123456') are accepted during account registration | The Sign Up form does not enforce password complexity rules, allowing users to register with extremely weak passwords. | The Password field on the Sign Up page lacks proper complexity validation (minimum length, uppercase, lowercase, number, special character). Testing confirms that simple numeric or short passwords such as '123456' or 'abcde' are accepted without any warning, which significantly weakens account security. | 1. User is on the Sign Up page. | 1. Navigate to the Sign Up page. 2. Enter Full Name: 'Weak Password User'. 3. Enter Email: 'weakpass.test@example.com'. 4. Enter Password: '123456'. 5. Confirm Password: '123456'. 6. Click 'Sign Up'. | Password: 123456 | System should reject the password and display a message such as 'Password must be at least 8 characters and include uppercase, lowercase, number, and special character.' | Account is created successfully with the weak password '123456' with no complexity warning shown. | High | High | Staging (https://tichi-app-webapp-stage.web.app) | Google Chrome v.126.0 (Latest) | Windows 11 (64-bit) | Build 1.4.2-stage | Open | QA Engineer - Manual Testing Team | 2026-06-20 | [Screenshot_BUG_005.png - to be attached] | Password policy to be enforced via shared validation library used across Login/Sign Up.
BUG_006 | TC_LOGIN_009 | Login | Error message not displayed when Password field is left blank | Submitting the Login form with an empty Password field does not display any validation error message to the user. | When a user provides a valid email but leaves the Password field empty and clicks 'Login', the form is submitted (or the button appears to do nothing) without any indication to the user of what went wrong. No inline error, toast, or highlighted field is shown. | 1. User is on the Login page. | 1. Navigate to the Login page. 2. Enter Email: 'validuser@example.com'. 3. Leave the Password field empty. 4. Click the 'Login' button. 5. Observe page response. | Email: validuser@example.com Password: (blank) | System should display an inline error: 'Password is required' and highlight the empty field in red. | No error message appears. The button either does nothing visibly or briefly shows a loading spinner with no follow-up feedback, leaving the user confused about the failure. | Medium | Medium | Staging (https://tichi-app-webapp-stage.web.app) | Google Chrome v.126.0 (Latest) | Windows 11 (64-bit) | Build 1.4.2-stage | Open | QA Engineer - Manual Testing Team | 2026-06-20 | [Screenshot_BUG_006.png - to be attached] | Will add inline validation message component; low effort fix.
BUG_007 | TC_SIGNUP_011 | Sign Up | Duplicate email registration does not show a clear error message | Attempting to sign up with an email address that is already registered results in a generic or unclear error, instead of a specific 'Email already exists' message. | When a user attempts to create a new account using an email address already associated with an existing account, the system should clearly inform the user that the email is already in use (and ideally suggest logging in instead). Currently, the form either fails silently, shows a generic 'Something went wrong' message, or shows a raw server error, none of which clearly communicate the actual cause to the end user. | 1. An account already exists with email 'existinguser@example.com'. 2. User is on the Sign Up page. | 1. Navigate to the Sign Up page. 2. Enter Full Name: 'Existing User'. 3. Enter Email: 'existinguser@example.com' (already registered). 4. Enter Password: 'ValidPass1!'. 5. Confirm Password: 'ValidPass1!'. 6. Click 'Sign Up'. | Email: existinguser@example.com (pre-existing account) | System should display a clear, user-friendly message: 'An account with this email already exists. Please log in or reset your password.' | System displays a generic error message ('Something went wrong, please try again') that does not indicate the email is already registered. | Medium | Medium | Staging (https://tichi-app-webapp-stage.web.app) | Google Chrome v.126.0 (Latest) | Windows 11 (64-bit) | Build 1.4.2-stage | Open | QA Engineer - Manual Testing Team | 2026-06-21 | [Screenshot_BUG_007.png - to be attached] | Backend returns generic 409 without message mapping; frontend needs to handle specific error codes.
BUG_008 | TC_LOGIN_015 | Login | Login page is vulnerable to SQL Injection via Email field | Entering SQL injection payloads into the Email field on the Login form does not throw a proper validation error and returns unexpected server behavior. | Security testing of the Login form's Email field using common SQL injection payloads (e.g., ' OR '1'='1) reveals that the input is not properly sanitized/escaped before being processed. While full authentication bypass was not confirmed, the server returned an inconsistent/verbose error response, indicating the input reaches the query layer without adequate sanitization, which is a security risk requiring immediate developer/security review. | 1. User is on the Login page. | 1. Navigate to the Login page. 2. In the Email field, enter: ' OR '1'='1 3. In the Password field, enter: ' OR '1'='1 4. Click 'Login'. 5. Observe server response (check network tab / response body). | Email: ' OR '1'='1 Password: ' OR '1'='1 | Input should be rejected by client-side email format validation before any request is sent. If sent, backend should sanitize input and return a generic 'Invalid credentials' response with no internal error details exposed. | Client-side validation does not block the payload from being submitted. Server response includes a verbose/technical error trace in some instances, suggesting insufficient input sanitization. | Critical | High | Staging (https://tichi-app-webapp-stage.web.app) | Google Chrome v.126.0 (Latest) | Windows 11 (64-bit) | Build 1.4.2-stage | Open | QA Engineer - Manual Testing Team | 2026-06-21 | [Screenshot_BUG_008.png - to be attached] | Escalated to security team - input sanitization review in progress. Marked as security-sensitive.
BUG_009 | TC_SIGNUP_014 | Sign Up | 'Confirm Password' field does not validate match with 'Password' field in real time | The Sign Up form does not show a real-time mismatch warning when the Confirm Password field does not match the Password field; the error only appears after form submission. | Best practice UX requires real-time (on-blur or on-keyup) validation feedback when passwords do not match, so users can correct the issue before submitting. Currently, the mismatch error only appears after the user clicks 'Sign Up', creating unnecessary friction and a full round trip for a client-side-detectable issue. | 1. User is on the Sign Up page. | 1. Navigate to the Sign Up page. 2. Fill in Full Name and Email fields with valid data. 3. Enter Password: 'Passw0rd!23'. 4. Enter Confirm Password: 'Passw0rd!24' (mismatched). 5. Click outside the Confirm Password field (blur event). 6. Observe whether any error appears before clicking Sign Up. | Password: Passw0rd!23 Confirm Password: Passw0rd!24 | An inline error such as 'Passwords do not match' should appear immediately after the user leaves the Confirm Password field, without requiring form submission. | No error is shown until the 'Sign Up' button is clicked, at which point the form submission is blocked and the error is finally displayed. | Low | Medium | Staging (https://tichi-app-webapp-stage.web.app) | Google Chrome v.126.0 (Latest) | Windows 11 (64-bit) | Build 1.4.2-stage | Open | QA Engineer - Manual Testing Team | 2026-06-22 | [Screenshot_BUG_009.png - to be attached] | Will add onBlur validation handler to Confirm Password field.
BUG_010 | TC_LOGIN_010 | Login | 'Forgot Password' link is not functional / does not navigate to reset flow | Clicking the 'Forgot Password?' link on the Login page does not redirect the user to the password reset page. | The 'Forgot Password?' hyperlink displayed below the Login form appears clickable (correct hover state/cursor) but clicking it does not perform any navigation or action. This blocks users who need to recover access to their account from doing so through the standard self-service flow. | 1. User is on the Login page. | 1. Navigate to the Login page. 2. Locate the 'Forgot Password?' link below the Login button. 3. Click the link. 4. Observe whether the page navigates or a modal opens. | N/A | Clicking 'Forgot Password?' should navigate the user to a password reset page/modal where they can enter their email to receive a reset link. | Clicking the link produces no visible action; the user remains on the same Login page with no navigation or modal triggered. | Critical | High | Staging (https://tichi-app-webapp-stage.web.app) | Google Chrome v.126.0 (Latest) | Windows 11 (64-bit) | Build 1.4.2-stage | Open | QA Engineer - Manual Testing Team | 2026-06-22 | [Screenshot_BUG_010.png - to be attached] | Link exists in DOM but onClick handler was never wired up during last refactor. Fix identified.
BUG_011 | TC_SIGNUP_002 | Sign Up | Full Name field accepts numeric and special characters | The Full Name field on the Sign Up form allows numbers and special symbols (e.g., '@', '#', '123') to be entered and submitted as a valid name. | The Full Name input should ideally restrict input to alphabetic characters, spaces, hyphens, and apostrophes to maintain data quality. Currently, the field accepts any character, including digits and special symbols, and successfully creates an account with a name like 'John123@#'. | 1. User is on the Sign Up page. | 1. Navigate to the Sign Up page. 2. Enter Full Name: 'John123@#'. 3. Enter a valid unique Email. 4. Enter a valid Password and Confirm Password. 5. Click 'Sign Up'. | Full Name: John123@# Email: john123test@example.com Password: Passw0rd!23 | System should reject non-alphabetic characters in the Full Name field and display 'Name should only contain letters and spaces.' | Account is created successfully with the Full Name stored as 'John123@#'. | Low | Low | Staging (https://tichi-app-webapp-stage.web.app) | Google Chrome v.126.0 (Latest) | Windows 11 (64-bit) | Build 1.4.2-stage | Open | QA Engineer - Manual Testing Team | 2026-06-23 | [Screenshot_BUG_011.png - to be attached] | Will add regex pattern restricting to letters, spaces, hyphens, apostrophes.
BUG_012 | TC_LOGIN_003 | Login | Login button remains enabled and clickable while API request is in progress | The 'Login' button does not get disabled during the authentication API call, allowing users to submit multiple duplicate login requests by clicking rapidly. | When a user clicks 'Login', the request to the authentication endpoint takes 1-3 seconds to resolve. During this time, the button remains active and clickable, and rapid repeated clicks trigger multiple simultaneous login requests, which can cause race conditions, duplicate session tokens, or unnecessary server load. | 1. User is on the Login page with valid credentials entered. | 1. Navigate to the Login page. 2. Enter valid Email and Password. 3. Click the 'Login' button rapidly 5 times in quick succession. 4. Monitor the Network tab in DevTools for duplicate requests. | Email: validuser@example.com Password: ValidPass1! | The 'Login' button should be disabled (and ideally show a loading spinner) immediately after the first click until the API response is received, preventing duplicate submissions. | The button stays enabled, and up to 5 duplicate POST requests to the login endpoint are observed in the Network tab. | Medium | Medium | Staging (https://tichi-app-webapp-stage.web.app) | Google Chrome v.126.0 (Latest) | Windows 11 (64-bit) | Build 1.4.2-stage | Open | QA Engineer - Manual Testing Team | 2026-06-23 | [Screenshot_BUG_012.png - to be attached] | Button disable-on-submit logic missing; straightforward fix.
BUG_013 | TC_SIGNUP_016 | Sign Up | Sign Up page layout breaks on mobile viewport (375px width) | The Sign Up form's input fields and 'Create Account' button overflow outside the visible viewport when the browser window is resized to a mobile width (375px), causing a horizontal scrollbar to appear. | Responsive design testing on a simulated mobile viewport (iPhone SE - 375x667) shows that the Sign Up form container does not resize appropriately. Input fields extend beyond the right edge of the screen, and the 'Create Account' button is partially cut off, requiring horizontal scrolling to access, which is a poor mobile UX. | 1. Browser DevTools is open with device toolbar/responsive mode enabled. | 1. Navigate to https://tichi-app-webapp-stage.web.app/signup 2. Open Chrome DevTools (F12) and enable Device Toolbar. 3. Set viewport to 375 x 667 (iPhone SE). 4. Observe the layout of the Sign Up form. | Viewport: 375px width | The Sign Up form should be fully responsive, with all fields and buttons fitting within the viewport width without horizontal scrolling. | Input fields and the 'Create Account' button overflow past the right edge of the screen; a horizontal scrollbar appears. | Medium | Medium | Staging (https://tichi-app-webapp-stage.web.app) | Google Chrome v.126.0 (Latest) | Windows 11 (64-bit) | Build 1.4.2-stage | Open | QA Engineer - Manual Testing Team | 2026-06-24 | [Screenshot_BUG_013.png - to be attached] | CSS flexbox issue on auth container; needs media query for widths below 400px.
BUG_014 | TC_LOGIN_018 | Login | Session persists after clicking 'Logout' in another browser tab (multi-tab session issue) | When a user logs out from one browser tab, other open tabs of the same application continue to show the user as logged in until manually refreshed. | With the application open in two browser tabs under the same logged-in session, logging out in Tab 1 does not propagate the logout state to Tab 2 in real time. Tab 2 continues to display authenticated content and allows navigation to protected pages until the user manually refreshes it, which is a session-management inconsistency. | 1. User is logged in. 2. Two browser tabs are open with the application, both authenticated. | 1. Log in to the application in Tab 1. 2. Open a new Tab 2 with the same application URL (session should carry over). 3. In Tab 1, click 'Logout'. 4. Switch to Tab 2 without refreshing. 5. Attempt to navigate to a protected page (e.g., Dashboard/Profile) in Tab 2. | N/A | Logging out in one tab should invalidate the session across all open tabs (via storage event listener or similar mechanism), redirecting other tabs to the Login page on next interaction. | Tab 2 remains on the authenticated view and allows navigation to protected pages until manually refreshed. | High | Medium | Staging (https://tichi-app-webapp-stage.web.app) | Google Chrome v.126.0 (Latest) | Windows 11 (64-bit) | Build 1.4.2-stage | Open | QA Engineer - Manual Testing Team | 2026-06-24 | [Screenshot_BUG_014.png - to be attached] | Requires BroadcastChannel or storage-event based session sync across tabs. Under investigation.
BUG_015 | TC_SIGNUP_006 | Sign Up | Terms and Conditions checkbox is not mandatory before account creation | Users can complete the Sign Up process and create an account without checking the 'I agree to the Terms and Conditions' checkbox. | The Sign Up form includes a checkbox for agreeing to Terms and Conditions / Privacy Policy, but this checkbox is not enforced as a mandatory field. Users can leave it unchecked and still successfully submit the form and create an account, which is a compliance/legal risk. | 1. User is on the Sign Up page. | 1. Navigate to the Sign Up page. 2. Fill in all required fields (Name, Email, Password, Confirm Password) with valid data. 3. Leave the 'I agree to Terms & Conditions' checkbox unchecked. 4. Click 'Sign Up'. | Terms checkbox: unchecked | The 'Sign Up' button should remain disabled, or an error should be shown: 'You must agree to the Terms and Conditions to continue.' | Account is created successfully even with the Terms and Conditions checkbox left unchecked. | High | Medium | Staging (https://tichi-app-webapp-stage.web.app) | Google Chrome v.126.0 (Latest) | Windows 11 (64-bit) | Build 1.4.2-stage | Open | QA Engineer - Manual Testing Team | 2026-06-25 | [Screenshot_BUG_015.png - to be attached] | Checkbox validation was removed accidentally during last release. Reverting.
BUG_016 | TC_LOGIN_020 | Login | Email field is case-sensitive, causing valid users to fail login | Users registered with a mixed-case email address (e.g., User@Example.com) cannot log in successfully when entering the same email in all lowercase. | Email addresses are case-insensitive per RFC standards for the local domain portion in practice, and most systems normalize email casing before comparison. The Login module currently performs an exact case-sensitive match against the stored email, causing legitimate users to receive an 'Invalid credentials' error if they type their email in different casing than used during registration. | 1. An account is registered with email 'User@Example.com'. | 1. Register a new account using Email: 'User@Example.com'. 2. Log out. 3. Navigate to the Login page. 4. Enter Email: 'user@example.com' (all lowercase). 5. Enter the correct password. 6. Click 'Login'. | Registered Email: User@Example.com Login attempt Email: user@example.com Password: (correct password) | Login should succeed regardless of email casing, as email addresses should be normalized to lowercase before comparison/storage. | Login fails with 'Invalid email or password' message when casing does not exactly match the registered value. | Medium | Medium | Staging (https://tichi-app-webapp-stage.web.app) | Google Chrome v.126.0 (Latest) | Windows 11 (64-bit) | Build 1.4.2-stage | Open | QA Engineer - Manual Testing Team | 2026-06-25 | [Screenshot_BUG_016.png - to be attached] | Will normalize email to lowercase on both client submission and backend comparison.
BUG_017 | TC_SIGNUP_019 | Sign Up | UI misalignment: 'Sign Up' and 'Login' tab switch buttons overlap on smaller desktop resolutions | At a browser resolution of 1024x768, the tab-switch buttons ('Login' / 'Sign Up') at the top of the authentication card visually overlap each other. | On smaller desktop resolutions (1024x768), the flex/grid layout of the Login/Sign Up toggle buttons does not wrap or shrink properly, causing the two buttons to overlap by approximately 10-15 pixels, making the 'Sign Up' label partially unreadable and difficult to click precisely. | 1. Browser window/resolution set to 1024x768. | 1. Resize the browser window to 1024x768 (or use DevTools responsive mode). 2. Navigate to https://tichi-app-webapp-stage.web.app 3. Observe the Login/Sign Up toggle tabs at the top of the auth card. | Resolution: 1024x768 | The 'Login' and 'Sign Up' toggle buttons should remain fully visible, properly spaced, and independently clickable at all supported resolutions. | The two buttons visually overlap, with 'Sign Up' text partially hidden behind the 'Login' button's right edge. | Low | Low | Staging (https://tichi-app-webapp-stage.web.app) | Google Chrome v.126.0 (Latest) | Windows 11 (64-bit) | Build 1.4.2-stage | Open | QA Engineer - Manual Testing Team | 2026-06-26 | [Screenshot_BUG_017.png - to be attached] | Will adjust min-width and gap properties on toggle button container for smaller resolutions.
BUG_018 | TC_LOGIN_014 | Login | Generic error message does not distinguish between 'wrong password' and 'user not found' | The Login form displays the same generic error for both a non-existent email and an incorrect password, which is acceptable for security but currently the message text is misleading ('Network error, please try again') rather than credential-related. | While intentionally generic credential error messages are a security best practice, the current implementation shows a technically incorrect message ('Network error, please try again') for invalid credential scenarios, even when there is no actual network issue. This misleads users into thinking there is a connectivity problem rather than a credentials issue, causing confusion and unnecessary retries/support tickets. | 1. User is on the Login page. | 1. Navigate to the Login page. 2. Enter Email: 'nonexistentuser@example.com' (not registered). 3. Enter any Password: 'RandomPass1!'. 4. Click 'Login'. 5. Observe the error message shown. | Email: nonexistentuser@example.com Password: RandomPass1! | System should display a clear, generic credentials-related message such as 'Invalid email or password. Please try again.' | System displays 'Network error, please try again,' which incorrectly implies a connectivity issue rather than an authentication failure. | Medium | Low | Staging (https://tichi-app-webapp-stage.web.app) | Google Chrome v.126.0 (Latest) | Windows 11 (64-bit) | Build 1.4.2-stage | Open | QA Engineer - Manual Testing Team | 2026-06-26 | [Screenshot_BUG_018.png - to be attached] | Message copy needs to be corrected; not a network error, mapping issue in error handler.
BUG_019 | TC_SIGNUP_009 | Sign Up | Leading/trailing whitespace in Email field is not trimmed before validation | Entering an email address with leading or trailing spaces (e.g., ' test@example.com ') is not trimmed automatically, causing unexpected validation or duplicate-account issues. | When a user accidentally includes a space before or after their email address during sign-up (common with copy-paste), the application does not trim the whitespace before validating or storing it. This can lead to the system treating ' test@example.com' and 'test@example.com' as two different accounts, or causing an otherwise valid email to fail format validation due to the extra whitespace. | 1. User is on the Sign Up page. | 1. Navigate to the Sign Up page. 2. In the Email field, enter: ' testuser@example.com' (note leading space, can be done via paste). 3. Fill remaining fields with valid data. 4. Click 'Sign Up'. | Email: ' testuser@example.com' (leading space) | The system should automatically trim leading/trailing whitespace from the Email field before validation and storage. | The email is either rejected as invalid due to the untrimmed space, or stored with the space intact, leading to potential duplicate-account/lookup issues. | Low | Low | Staging (https://tichi-app-webapp-stage.web.app) | Google Chrome v.126.0 (Latest) | Windows 11 (64-bit) | Build 1.4.2-stage | Open | QA Engineer - Manual Testing Team | 2026-06-27 | [Screenshot_BUG_019.png - to be attached] | Will add .trim() to email input before validation and submission.
BUG_020 | TC_LOGIN_022 | Login | Page does not display a loading indicator during login API call | After clicking 'Login', there is no visual feedback (spinner/loader) indicating that a request is being processed, making the app feel unresponsive on slower connections. | On slower network conditions (throttled to 'Slow 3G' in DevTools), clicking 'Login' produces no immediate visual feedback for 2-4 seconds. Users are likely to assume the click did not register and may click multiple times, compounding other issues such as BUG_012 (duplicate submissions). | 1. Network throttling set to 'Slow 3G' in Chrome DevTools. 2. User is on the Login page with valid credentials entered. | 1. Open Chrome DevTools > Network tab > set throttling to 'Slow 3G'. 2. Navigate to the Login page. 3. Enter valid Email and Password. 4. Click 'Login'. 5. Observe the button/page for any loading state during the delay. | Network throttle: Slow 3G | A loading spinner or disabled-button state with 'Logging in...' text should appear immediately after clicking, until the response is received. | No loading indicator is shown; the button and page appear static/unresponsive during the 2-4 second delay. | Low | Medium | Staging (https://tichi-app-webapp-stage.web.app) | Google Chrome v.126.0 (Latest) | Windows 11 (64-bit) | Build 1.4.2-stage | Open | QA Engineer - Manual Testing Team | 2026-06-27 | [Screenshot_BUG_020.png - to be attached] | Adding loading spinner state tied to API call promise lifecycle.
BUG_021 | TC_SIGNUP_021 | Sign Up | Password strength meter does not update correctly when password is edited (paste vs type) | The password strength indicator on the Sign Up form only updates when the user types character-by-character; pasting a password does not trigger a strength recalculation. | The visual password strength meter (Weak/Medium/Strong bar) relies on a 'keyup' or 'input' event that does not fire correctly when a password is pasted via Ctrl+V or right-click paste. As a result, users who paste a strong, randomly generated password (e.g., from a password manager) see the meter incorrectly remain at 'Weak' or blank, which could mislead users into thinking their strong password is insufficient. | 1. User is on the Sign Up page. 2. A strong password is available in the clipboard (e.g., 'Xk9$mP2vLq8!Rz'). | 1. Copy a strong password to clipboard: 'Xk9$mP2vLq8!Rz'. 2. Navigate to the Sign Up page. 3. Click on the Password field. 4. Paste the password using Ctrl+V. 5. Observe the password strength meter below the field. | Password (pasted): Xk9$mP2vLq8!Rz | The password strength meter should recalculate and correctly display 'Strong' immediately after the paste action, matching the actual password entered. | The strength meter remains blank or shows 'Weak' after pasting, only updating correctly if the user subsequently types an additional character manually. | Low | Low | Staging (https://tichi-app-webapp-stage.web.app) | Google Chrome v.126.0 (Latest) | Windows 11 (64-bit) | Build 1.4.2-stage | Open | QA Engineer - Manual Testing Team | 2026-06-28 | [Screenshot_BUG_021.png - to be attached] | Paste event listener missing; will bind 'input' event instead of 'keyup' for strength meter.
BUG_022 | TC_LOGIN_025 | Login | Pressing 'Enter' key does not submit the Login form | After filling in Email and Password fields, pressing the 'Enter' key on the keyboard does not trigger form submission; users must click the 'Login' button explicitly. | Standard web form UX expects that pressing 'Enter' while focused within a form (especially the last field) submits that form. On the Login page, pressing 'Enter' after entering the password does nothing, which is an accessibility and usability gap, particularly for keyboard-only and power users. | 1. User is on the Login page. | 1. Navigate to the Login page. 2. Click into the Email field and enter a valid email. 3. Press 'Tab' to move to the Password field and enter a valid password. 4. Press the 'Enter' key on the keyboard (do not click the Login button). 5. Observe whether the form submits. | Email: validuser@example.com Password: ValidPass1! | Pressing 'Enter' while focused in the Password field should submit the Login form, identical to clicking the 'Login' button. | Pressing 'Enter' has no effect; the form does not submit and no request is sent until the user manually clicks the 'Login' button. | Medium | Low | Staging (https://tichi-app-webapp-stage.web.app) | Google Chrome v.126.0 (Latest) | Windows 11 (64-bit) | Build 1.4.2-stage | Open | QA Engineer - Manual Testing Team | 2026-06-28 | [Screenshot_BUG_022.png - to be attached] | Form submit handler needs onKeyDown listener for Enter key, or should default to form submit behavior.
BUG_023 | TC_SIGNUP_024 | Sign Up | Browser autofill overlaps placeholder text on Email field in Chrome | When Chrome's autofill suggestion dropdown is triggered on the Sign Up Email field, the yellow autofill background color overlaps and obscures the field's floating label, creating a visually broken appearance. | Chrome applies a default yellow background (#FAFFBD) to autofilled input fields, which has not been overridden with a custom CSS autofill style in the Sign Up form. This causes the floating label/placeholder text to become nearly unreadable against the yellow background, and is visually inconsistent with the rest of the form's design language. | 1. Chrome has at least one saved email/password combination for autofill. 2. User is on the Sign Up page. | 1. Navigate to the Sign Up page in Chrome. 2. Click on the Email field. 3. Select a suggested autofill entry from the dropdown, or allow Chrome to autofill the field. 4. Observe the background color and label readability of the field. | N/A (Chrome autofill behavior) | The Email field should retain the application's standard input styling (white/theme background, readable label) even when autofilled by the browser, using a CSS autofill override (e.g., -webkit-box-shadow trick). | The field background turns bright yellow and the floating label text becomes low-contrast and difficult to read. | Low | Low | Staging (https://tichi-app-webapp-stage.web.app) | Google Chrome v.126.0 (Latest) | Windows 11 (64-bit) | Build 1.4.2-stage | Open | QA Engineer - Manual Testing Team | 2026-06-29 | [Screenshot_BUG_023.png - to be attached] | Will add -webkit-autofill CSS override to match design system.
BUG_024 | TC_LOGIN_030 | Login | Copy-pasted password with trailing newline character causes login failure | Pasting a password that was copied along with an accidental trailing newline character (common when copying from a text file or notes app) causes login to fail with no indication of why. | When a password is copied from a source that includes a trailing newline/carriage return character, pasting it into the Password field on Login includes the invisible character. The system does not trim this whitespace/newline before sending the login request, resulting in an 'Invalid credentials' error even though the visible password appears correct, confusing the user. | 1. A valid registered account exists. 2. Password text with trailing newline is available in clipboard. | 1. Copy the text 'ValidPass1!\n' (password followed by a newline) from a text editor. 2. Navigate to the Login page. 3. Enter the registered Email. 4. Paste the copied password into the Password field. 5. Click 'Login'. | Email: validuser@example.com Password (pasted, with trailing newline): 'ValidPass1!\n' | The system should trim leading/trailing whitespace and newline characters from the password input before submission, or at minimum, provide clear feedback if unusual characters are detected. | Login fails with a generic 'Invalid email or password' message, with no indication that a hidden newline character caused the mismatch. | Low | Low | Staging (https://tichi-app-webapp-stage.web.app) | Google Chrome v.126.0 (Latest) | Windows 11 (64-bit) | Build 1.4.2-stage | Open | QA Engineer - Manual Testing Team | 2026-06-29 | [Screenshot_BUG_024.png - to be attached] | Will add trim() on password field before submission; also validate for control characters.
BUG_025 | TC_SIGNUP_027 | Sign Up | Sign Up success confirmation message disappears too quickly (auto-dismiss toast) | After successful account registration, the success toast notification ('Account created successfully!') auto-dismisses after approximately 1 second, which is too fast for most users to read. | The success toast/snackbar shown after a successful Sign Up is configured with an auto-dismiss timeout that appears to be around 1000ms, significantly shorter than the generally recommended 3-5 seconds for toast notifications. Users with slower reading speed or those who look away briefly may miss the confirmation entirely, causing uncertainty about whether their account was actually created. | 1. User has filled out the Sign Up form with valid, unique data. | 1. Navigate to the Sign Up page. 2. Fill in all fields with valid, unique data. 3. Click 'Sign Up'. 4. Time how long the success toast/message remains visible on screen using a stopwatch. | N/A | The success confirmation toast should remain visible for at least 3-5 seconds before auto-dismissing, per standard UX guidelines. | The toast notification disappears after approximately 1 second, which is too brief for reliable readability. | Low | Low | Staging (https://tichi-app-webapp-stage.web.app) | Google Chrome v.126.0 (Latest) | Windows 11 (64-bit) | Build 1.4.2-stage | Open | QA Engineer - Manual Testing Team | 2026-06-30 | [Screenshot_BUG_025.png - to be attached] | Toast duration configuration will be updated from 1000ms to 4000ms per UX guidelines.